## Front End
Mobile App _ Front End/Native App Client
Task ID | Task Name | days | Status
System SetUp
| Set up the visual studio for xamarin forms. | 1 | Done
| Set up the visual studio for xamarin forms. | 0.5 | Done
Global requirement
| Integrate the Appliation icon for Android platform | 0.25 | Done
| Integrate the Appliation icon for iOS platform | 0.5 | Done
| Integrate the Splash screen for the Android platform | 0.5 | Done
| Integrate the Splash screen for the iOS platform | 0.5 | Done
| Implementation for network availiability check | 0.25 | Done
SCREENS
Login Screen
| Design the UI for the screen | 1 | Done
| Create the model for and bind the screen with model | 0.5
| Create the view-model and business logic for the screen(bindings, navigation, add the validation for login page, etc.) | 0.5
| Analyze the api request/response for login page | 0.25
| Add the business logic to Integrate the basic login api | 0.5
| Create and bind the models for login api json request and response handle | 0.5
| Make screen UI compatible with iOS platform | 0.5
| unit testing for screen | 1
SignUp Screen
| Design the UI for the screen | 1
| Create the model for and bind the screen with model | 0.25
| Create the view-model and business logic for the screen(bindings, navigation, add the validation for SingUp page, etc.) | 0.75
| Add the business logic to Integrate the Singup api | 0.5
| Create and bind the models for Signup api json request and response handle | 0.5
| Make screen UI compatible with iOS platform | 1
| unit testing for screen | 1
Forgot Password screen
| Design the UI for the screen | 0.75
| Create the model for and bind the screen with model | 0.5
| Create the view-model and business logic for the screen(bindings, navigation, add the validation, etc.) | 0.75
| Implementation for reset/forgot password feature. | 2 | How app will allow user to reset password?
| unit testing for screen | 1
Main Screen After Login
| Design the UI for the screen | 1.5
| Create the model for and bind the screen with model | 0.5
| Create the view-model and business logic for the screen(bindings, navigation etc.) | 0.5
| Add the business logic to Integrate the list of items API | 0.5
| Create and bind the models for list api json request and response handle | 0.5
| Implementation of parse and retreive & binding of the grocery items in the list into list view format | 0.5
| Make screen UI compatible with iOS platform | 1
| unit testing for screen | 1
Add item Screen
| Design the UI for the screen | 1.25
| Create the model for and bind the screen with model | 0.5
| Create the view-model and business logic for the screen(bindings, navigation etc.) | 0.75
| Add the business logic to Integrate the API. | 0.75
| Create and bind the models for list api json request and response handle | 0.75
| Make screen UI compatible with iOS platform | 1
| unit testing for screen | 1
Edit item Screen
| Design the UI for the screen | 0.5
| Create the model for and bind the screen with model | 0.5
| Create the view-model and business logic for the screen(bindings, navigation etc.) | 0.5
| Add the business logic to Integrate the API. | 0.5
| Create and bind the models for list api json request and response handle | 0.5
| Make screen UI compatible with iOS platform | 1
| unit testing for screen | 1

## Back End End
Mobile App - BACK END API
Task ID | Task Name | days | Status
| Set up the visual studio for web api | 1 | Done
| Set up the sql server / sqllite for database integration | 1 | Done
Global requirement
| create the architecture and have the common file configuration. | 2 | Done
Login API
| Create model for handle the request and response. | 1
| Create the view model and business logic for Login screen. | 1
| Create the binding the sql server to insert/ ge the data. | 1.25
| Create the binding with database in DAL | 1
| Create the login table in sql server database. | 1
| Unit test the login API with postman | 1
SignUp / Registration API
| Create model for handle the request and response. | 1 | Done
| Create the view model and business logic for sign up screen | 1 | Done
| Create the binding the sql server to insert/ ge the data. | 1 | Done
| Create the binding with database in DAL | 1 | Done
| Create the login table in sql server database. | 1 | Done
| Unit test the login API with postman | 1 | Done
Forgot Password API
| Create model for handle the request and response. | 1
| Create the view model and business logic for forgot password. | 1
| Create the binding the sql server to insert/ ge the data. | 1
| Create the binding with database in DAL | 1.5
| Create the login table in sql server database. | 1.5
| Unit test the login API with postman | 1
Main Screen After Login
| Create model for handle the request and response. | 1
| Create the view model and business logic for main screen. | 1
| Create the binding the sql server to insert/ ge the data. | 2
| Create the binding with database in DAL | 2
| Create the login table in sql server database. | 2
| Unit test the login API with postman | 1
Add item Screen
| Create model for handle the request and response. | 1
| Create the view model and business logic for add item screen. | 1
| Create the binding the sql server to insert/ get the data. | 2
| Create the binding with database in DAL | 2
| Create the login table in sql server database. | 2
| Unit test the login API with postman | 1
Edit item Screen
| Create model for handle the request and response. | 1
| Create the view model and business logic for add item screen. | 1
| Create the binding the sql server to insert/ get the data. | 1
| Create the binding with database in DAL | 1
| Create the login table in sql server database. | 1
| Unit test the login API with postman | 1

## Chat and Payment Gateway
Payment Gateway Screen (Time may vary for this)
Analyse the payment gateway method | 2
Create UI for the payment screen. | 2.5
create Business logic and models and to bind the data with view model | 1.5
Integrate the payment gateway SDK for Android | 1.5
Integrate the payment gateway SDK for iOS. | 2
Create API request response for payment gateway. | 1.5
unit testing for screen. | 1
Chatting Functionality(Signal R Implementation)
Work on to analyse the signal r functionality for end to end chat. | 3
Design the UI for the screen | 3
Create the signal R hub | 2
Configure the project to use signal r | 2
create business logic and models and bind the data with view model. | 1
Work on to implement the signal r functionality on iOS platform. | 5
Payment Gateway Screen**
Analyze the payment gateway integration | 3
create the model to handle the request and response | 1
work on to integrate the payment sdk with PCI compliant | 2
Chatting Functionality(Signal R Implementation)
Analyse the signal r functionality for web | 2
create the signal R hub | 3
create the view model and business logic for signal r | 2
create the binding with database in DAL | 1
Create the database tab;le in sql server database | 2
create an api to save the end to end chat | 1
unit testing the signal r functionality with popstman